## Slide 1: Project RS(3R), Kolkata Monthly (Dec-2022) FRACAS Meeting
Notes: 1

## Slide 2: CONTENTS
Train Summary
SYSTEM RELEVANT & SERVICE FAILURES
service Failure Detail and Action Plan
RUNNING MILEAGE
Reliability performance (MDBF)
MDBCF
Pattern Failure
Availability

## Slide 3
Depot | No. of Trains Under Commissioning (Not started revenue service) | No. of Trains Under Stabilization (Until 6 months from start of each train’s revenue service) | No. of Trains Under Reliability Verification | DLP Over trains | Total No. of Trains
CPD | 3 | 0 | 5 | 6 | 14
1) Train summary

## Slide 4
2) SYSTEM RELEVANT & SERVICE FAILURES
Period: OCT’22 onwards
Sr. no | Systems | Relevant Failures |  |  |  | Service Failures |  |  | 
 |  | Oct’22 | Nov'22 | Dec'22 | TOTAL | Oct'22 | Nov'22 | Dec’22 | TOTAL
1 | Propulsion System |  |  |  |  |  |  |  | 
2 | Auxiliary Supply System |  |  |  |  |  |  |  | 
3 | Air Supply and Friction Brake Equipment |  |  |  |  |  |  |  | 
4 | Door System |  |  |  |  |  |  |  | 
5 | HVAC System |  |  |  |  |  |  |  | 
6 | Communication System |  |  |  |  |  |  |  | 
7 | Couplers and Draft Gear |  |  |  |  |  |  |  | 
8 | Bogies & Suspension |  |  |  |  |  |  |  | 
9 | Lighting System |  |  |  |  |  |  |  | 
10 | TCMS |  |  |  |  |  |  |  | 
11 | Fire Detection System |  |  |  |  |  |  |  | 
12 | Structure and Interior Fittings |  |  |  |  |  |  |  | 
13 | Wiper |  |  |  |  |  |  |  | 
TOTAL |  |  |  |  |  |  |  |  | 

## Slide 5
SYSTEM RELEVANT Failures
Chart: Relevant Failure
| Propulsion System | Auxiliary Supply System | Air Supply and Friction Brake Equipment | Door System | HVAC System | Communication System | Couplers and Draft Gear | Bogies & Suspension | Lighting System | TCMS | Fire Detection System | Structure and Interior Fittings | Wiper
Relevant Failures Oct'22 | 23 | 0 | 7 | 32 | 29 | 14 | 0 | 4 | 5 | 9 | 19 | 22 | 22
Relevant Failures Nov'22 | 20 | 6 | 12 | 25 | 16 | 19 | 0 | 10 | 10 | 12 | 11 | 16 | 17
Relevant Failures TOTAL

## Slide 6: 3) service Failure Detail and Action Plan
SERVICE FAILURE TYPE | FAILURE DATE | TS# | CAR NO | System | FAULT DESCRIPTION | MAIN LINE ACTION | DEPOT ACTION | PLAN TO ADDRESS ISSUE
Deboarding | 04.11.2022 | TS#02 | DM1 | Propulsion System | Motoring not possible and EB by CC between DIN-KUR DN mast no. 07/42 | 19:42 Hrs: TS#02 (ID03) at mast no 7/42 between DIN DN - KUR DN train stuck due to EB by CC ( other cab activated fault on TCMS as per TO, Cab was not getting enabled and motoring not possible from DM1 19:44 Hrs: As per RSC changed mode of train to RM & checked motoring is possible or not? TS 02 informed motoring not possible in RM. 19:48 Hrs: RSC instructed to change cab. 19:50 Hrs: Activated DM6 cab & EB got reset. 19:52 Hrs: Cab changed again & key inserted in DM1 cab & showing cab not activated. 19:54 Hrs: Motoring not possible in RM mode due to cab not enable 19:57 Hrs: As per RSC limp home activated by pressing push button only and got motoring. Train authorized in RM till KUR DN 20:01 Hrs: Train reached at KUR DN doors open in standby mode. TO reported that doors are not closing now. 20:01 Hrs: Train evacuated at KUR DN. 20:05 Hrs: As per RSC instructed TO to AUX off the train. 20:06 Hrs: Train AUX off 20:10 Hrs: Train AUX ON & motoring is possible in RM so departed train from KUR DN. 20:15 Hrs: TO reported ATP available so departed that train in ATP. Instructed TO to skip all station till DAH as per skip procedure. | As per ER data: DM1 cab was activated at 19:31:26 hrs for movement in DN Line. At 19:41:01.088 (at Train speed 54.4 kmph) all signals in DM1 car RIO1 YDA1 and YDA2 status along with YGA status was unknown for 500 millisecs and got normal at 19:41:01.688 millisecs. Due to above following signals got unknown on ER data for 500 millisecs: 1.Mode Selector position(OFF/REV/STANDBY/FWD/ATP/ATO) 2.Door Open PB status 3.Key switch ON Relay status 4.Powering and Braking T/L, EBVR, DPR,DPLCOS etc. During above time all YDA1 and YDA2 and YGA signals in RIO2 was normal. At 19:41:01.088 when above status got unknown EB command was applied by TCMS (ConTFCS signal changed to 6) although EBVR was energized. Due to TCMS EB command Train speed started to decrease and Train stopped at 19:41.17 hrs. As per MDCU data at 19:42:25.950 “KSONR and KOFFR not energized and Key inserted in DM1” message appeared and cleared at 19:44:50.550 hrs although Key switch was ON and KSONR was energized. After this TO deactivated and again activated Cab twice but EB by TCMS was not released. As per Mainline reporting at 19:57:22 Train movement was possible by pressing Limp Home PB (at this time also TCMS was giving EB command as per data). At 20:00:37.888 Train stopped at KUR DN and Doors were opened at 20:01:50 hrs(TDCLR dropped to 0) and was not energized although TO tried Door closing through PB. At 20:05:56 Trains was made AUX OFF and AUX ON. TDCLR was energized at 20:12:23.564 hrs and EB was released. After this movement was possible normally in TCMS mode. Depot Action:- Motoring from DM1 side we check motoring from both side found normal also during multiple times operation of Key switch ON & OFF found ok. | Hitachi will address this issue in new platform level software, which is already uploaded in TS#21.
Withdrawl | 12.11.2022 | TS#15 | DM1 | TCMS | Desk command (motor -brk) minor fault DM1 (VCB opened T2 car and motors in DM1 & M3 CAR showing Faulty ) | VCB not getting closed through TCMS command .physically both VCB open/close command given then both VCB closed at AAR DN PF Again the same fault appeared at neutral section between OVA DN- DAE DN ,VCB (T2 car) was not getting closed till DAE DN PF further physically VCB open/close command given then both VCB got closed and motors got healthy .further same fault logged at BOW DN-PAE DN this time VCB is not getting closed by any way hence train run to DAH 3rd with single VCB closed. | As per MDCU & ER data: As per data it is observed that, at 13:20:59.989 hrs Train started moving in ATP mode from OVA DN Pf. Due to neutral section (between OVA-DN- DAE DN) T2 car TCMS_VCB_Open cmd high at 13:21:32.089 hrs and VCB got open at 13:21:32.289. ACVR_STS become “zero” at 13:21:33.789 hrs. After neutral section at 13:21:35.489 hrs T2 car VCB close cmd from TCMS was high, but VCB was not getting close. (VCB_STS becomes high for 100 ms) Further at 13:22:43.189 hrs TO tried to close T2 car VCB from TCMS VDU cmd, but still VCB was not getting close. Due to 02 times operations of VCB within 03 mins, “CI:Discharge system overheat in DM1/M3” were logged in MDCU data. From 13:22:50.689 hrs to 13:26:27.989 hrs TO tried several times to close T2 car VCB from TCMS VDU cmd as well as VCB push button, but still same issue persist. At 13:30:07.189 hrs TO again tried to close T2 car VCB from TCMS VDU cmd, VCB get close and coach working normal. At 13:39:34.689 hrs between BOW DN -PAE DN neutral section T2 car VCB got open through TCMS open cmd. After NS VCB close command high at 13:39:37.489, but VCB was not getting close. Further TO tried to close the VCB from TCMS VDU cmd as well as VCB push button, but still same issue persist. Depot Action: In depot we checked CI data, after analyzing data multiple times, VCB close command given within short duration of time, hence in unit 1 all motors showing faulty and VCB not getting closed, and observed that T2 car VCB pressure found low (i.e. 4.8 bar). Further Hitachi checked VCB box found Air leakage through PRV (pressure Relief Valve). For the same PRV regulator kit has been replaced and VCB pressure regulator setting set to 6.2 bar. VCB manual open/close operation checked for multiple times found normal. | 1) To address this issue HECP has been proposed by M/s Hitachi. 2) As decided M/s Hitachi will install 5 nos Shavo make PRV on trial basis.

## Slide 7
3) service Failure Detail and Action Plan
SERVICE FAILURE TYPE | FAILURE DATE | TS# | CAR NO | System | FAULT DESCRIPTION | MAIN LINE ACTION | DEPOT ACTION | PLAN TO ADDRESS ISSUE
Withdrawl | 12.11.2022 | TS#02 | DM6 | Door | DM6 partition door not closing | On primary investigation MA latch lock found faulty ,Which need to replace from spare. | In Depot investigation MA latch lock spring found broken.same has been replaced from spare .Further door lock operation found ok. | 1.M/s Saira performing lock duty cycle test for spring and operation of both master and emergency leaf . 2. Please find primary report in attachment.
Delay | 02.11.2022 | TS#04 | T2 | Door | Door B2 T2-Door failed to close due to obstruction | 07:13 @DAH UP TO reported same issue but same door closed after Reopening & closing 07:15 @KAW UP issue occurred again & same action repeated. @PAE UP This door opening & Closing operation is normal 07:19 @BOW UP issue was reported again so again saloon doors opened & closed but still door closing status not available so instructed TO & onboard RS staff to isolate the door from TCMS & mechanically. Same train kept as HSB train at DAH 3rd PF for attention. T2 car B2 Door fault attention completed jointly by RS & BEML staff. Also checked door operation multiple times and found normal. | As per MDCU Data: "Door B2 T2 - Door failed to close due to obstruction" logged at 07:13:02hrs and cleared at 07:13:24hrs. Again fault occurred "Door B2 T2 - Door failed to close due to obstruction" logged at 07:15:13hrs and cleared at 07:15:38hrs. Again, "Door B2 T2 - Door failed to close due to obstruction" logged at 07:19:39hrs and cleared at 07:19:57hrs. Mainline Action: Checked and found DCS cam slightly bend at right side door same has been rectified and 20 times operation done working normal. Depot Action: Door parameters found in limit. | 1). Suspected cause of DCS cam bending is gap between DCS cam plate and coving panel lock is less 2). As already square key lock holding plate modification has been done in all trains.
Delay | 01.11.2022 | TS#10 | T2 | Door | Door A3 T2 - Door Failed to close due to Obstruction Door A3 T2 - Major Fault (Wired) | As Fault reported, so RS Staff given reset to EDCUCB of same door but still same issue persist & ADCL was not available. So Instructed TO & RS Staff for isolate the A3 door of T2 car Physically & to keep EDCUCB in off condition at OVA DN as same door is not getting close properly. after isolating same door ADCL became available & Train departed from OVA DN. At 09:10 DAE DN again ADCL from T2 car was not available so same door mechanical locking reopened & closed then ADCL became available & train departed. at DAH 3rd PF same issue jointly attended by RS & BEML staff after that issue cleared. Now T2 car A3 Door operation is normal. | As per MDCU: "Door A3 T2 - Door failed to close due to obstruction" logged at 09:00:53hrs and cleared at 09:39:02hrs. "Door A3 T2 - Major fault (wired)" logged at 09:05:33hrs and cleared at 09:39:01hrs. "Door A3 T2 Emergency handle activation (wire)" logged at 09:05:34hrs and cleared at 09:05:34hrs. "Door A3 T2 TRDP communication missing" logged at 09:05:36hrs and cleared at 09:39:02hrs. Depot Action: Checked and found DCS cam found bent and coving panel plate hitting on left side DCS cam. same has been rectified and several time operation checked no abnormality found. | 

## Slide 8
4) RUNNING MILEAGE FOR ALL FLEET
 | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22 | Dec’22
Monthly |  |  |  |  |  |  |  |  | 
 | 92,333 | 97,951 | 92,980 | 94,758 | 97,484 | 104,374 | 112,561 | 106,394 | 
Accumulated |  |  |  |  |  |  |  |  | 
Line 2A & 7 | 92,333 | 190,284 | 283,264 | 378,022 | 475,506 | 579,880 | 692,441 | 798,835 | 
Total | 92,333 | 190,284 | 283,264 | 378,022 | 475,506 | 579,880 | 692,441 | 798,835 | 
Average running mileage (per train/Month) | 8,394 | 8,905 | 7,748 | 7,289 | 7,499 | 6,958 | 7,035 | 6,258 | 
Average running mileage (per train/day) | 280 | 287 | 258 | 235 | 242 | 232 | 227 | 209 | 

## Slide 9
RUNNING MILEAGE FOR CPD dEPOT
Train set | Start of Revenue Service | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
 |  | 1M | 2M | 3M | 4M | 5M | 6M | 7M | 8M
TS#01 | 14-02-2020 |  |  |  |  |  |  |  | 
TS#02 | 14-02-2020 |  |  |  |  |  |  |  | 
TS#03 | 14-02-2020 |  |  |  |  |  |  |  | 
TS#04 | 14-02-2020 |  |  |  |  |  |  |  | 
TS#05 | 14-02-2020 |  |  |  |  |  |  |  | 
TS#06 | 14-02-2022 |  |  |  |  |  |  |  | 
TS#07 | 20-10-2020 |  |  |  |  |  |  |  | 
TS#08 | 05-12-2020 |  |  |  |  |  |  |  | 
TS#09 | 27-08-2021 |  |  |  |  |  |  |  | 
TS#10 | 13-07-2022 |  |  |  |  |  |  |  | 
TS#11 | 13-07-2022 |  |  |  |  |  |  |  | 
TS#12 | NOT STARTED YET |  |  |  |  |  |  |  | 
TS#13 | NOT STARTED YET |  |  |  |  |  |  |  | 
TS#14 | NOT STARTED YET |  |  |  |  |  |  |  | 

## Slide 10
5) Reliability performance for line 2a & 7
(MDBF)
Running Mileage |  |  |  |  |  |  |  | 
Months | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
Lines | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7
Trains in reliability performance | 11 | 11 | 12 | 13 | 13 | 15 | 16 | 17
6M Running Mileage ( Km ) | 92333 | 190284 | 283264 | 378022 | 475506 | 579880 | 600108 | 608551
No of Service Failures (Pre-departure withdrawal, withdrawal , 3 min delay) |  |  |  |  |  |  |  | 
Months | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
Lines | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7
Monthly ( Failures ) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5
6 Months ( Failures ) | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7
Shortfall Trains from Availability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
MDBF |  |  |  |  |  |  |  | 
Months | Apr'22 | May'22 | Jun'22 | Jul'22 | Aug'22 | Sep'22 | Oct'22 | Nov'22
Lines | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7 | 2A & 7
Target MDBF | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Monthly MDBF (Train km) | - | - | - | - | - | - | 56281 | 21279
6 Months MDBF (Train km) |  |  |  |  |  |  | 300054 | 86936
Final 6M MDBF with Shortfall TS. |  |  |  |  |  |  | 300054 | 76069

## Slide 11
6) mdbcf of Reliability verification trains (MDBF 100,000 km)
System/Subsystem / Equipment/Component | Target | MDBCF | Result | 6M failure | Nov/22 |  | System/Subsystem / Equipment/Component | Target | MDBCF | Result | 6M failure | Nov/22
Propulsion System | 100,000 | 13,934 | Fail | 37 | 12 |  | Door System | 50,000 | 8,738 | Fail | 59 | 27
a) Pantograph | 1,500,000 | No Failure | Pass | 0 | 0 |  | a) EDCU | 5,000,000 | 2,749,712 | Fail | 9 | 2
b) VCB and Earthing switch | 9,300,000 | No Failure | Pass | 0 | 0 |  | b) Motor assembly | 70,000,000 | 24,747,408 | Fail | 1 | 1
c) Main Transformer | 61,600,000 | No Failure | Pass | 0 | 0 |  | c) Coupling assembly | 70,000,000 | No Failure | Pass | 0 | 0
d) Power Converter-Inverter | 1,360,000 | 2,062,284 | Pass | 1 | 0 |  | d) DLS | 80,000,000 | 24,747,408 | Fail | 1 | 0
e) Traction Motor | 40,800,000 | No Failure | Pass | 0 | 0 |  | e) DCS | 80,000,000 | 12,373,704 | Fail | 2 | 0
f) Arrester | 10,000,000 | No Failure | Pass | 0 | 0 |  | f) EDS | 40,000,000 | No Failure | Pass | 0 | 0
g) Potential transformer | 10,000,000 | No Failure | Pass | 0 | 0 |  | g) LOS | 40,000,000 | 8,249,136 | Fail | 3 | 0
h) Current transformer | NA | NA | NA | 0 | 0 |  | h) Saloon to cab door | 5,000,000 | 60,655 | Fail | 17 | 7
i) Master Controller | 1,000,000 | 1,031,142 | Pass | 1 | 1 |  | i) Emergency door | 1,000,000 | 1,031,142 | Pass | 1 | 0
j) Others | NA | NA | NA | 35 | 11 |  | j) Others | NA | NA | NA | 25 | 17
Auxiliary Supply System | 450,000 | 257,786 | Fail | 2 | 2 |  | HVAC System | 250,000 | 11,457 | Fail | 45 | 15
a) Auxiliary Converter-Inverter | 1,890,000 | No Failure | Pass | 0 | 0 |  | a) Compressor | 7,000,000 | No Failure | Pass | 0 | 0
b) Battery Charger | 5,060,000 | No Failure | Pass | 0 | 0 |  | b) Condenser coil | 7,000,000 | No Failure | Pass | 0 | 0
c) Back-up Batteries | 10,000,000 | 1,031,142 | Fail | 1 | 1 |  | c) Dryer | 20,000,000 | 24,747,408 | Pass | 1 | 0
d) Others | NA | NA | NA | 1 | 1 |  | d) Evaporator coil | 20,000,000 | No Failure | Pass | 0 | 0
Air Supply and Friction Brake Equipment | 70,000 | 27,135 | Fail | 19 | 12 |  | e) High pressure switch | 20,000,000 | No Failure | Pass | 0 | 0
a) Main Compressor | 1,500,000 | No Failure | Pass | 0 | 0 |  | f) Low pressure switch | 20,000,000 | No Failure | Pass | 0 | 0
b) Air Dryer Unit | 4,500,000 | No Failure | Pass | 0 | 0 |  | g) Condenser fan | 20,000,000 | 12,373,704 | Fail | 1 | 0
c) Aux Compressor | 8,000,000 | No Failure | Pass | 0 | 0 |  | h) Evaporator fan | 20,000,000 | No Failure | Pass | 0 | 0
d) Hose pipe | 10,000,000 | No Failure | Pass | 0 | 0 |  | i) Inverter for compressor | 7,000,000 | 12,373,704 | Pass | 2 | 0
e) BCU | 2,800,000 | No Failure | Pass | 0 | 0 |  | j) Air conditioning control panel | 10,000,000 | No Failure | Pass | 0 | 0
f) Precontrol valve | 20,000,000 | No Failure | Pass | 0 | 0 |  | k) Smoke detector unit | 20,000,000 | 171,857 | Fail | 6 | 0
g) BECU | 1,000,000 | No Failure | Pass | 0 | 0 |  | l) Others | NA | NA | NA | 35 | 15
h) Tread Brake Unit | 25,000,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
i) Anti-Skid Valve | 80,000,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
j) Levelling Valve | 70,000,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
k) TYFON | 30,000,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
l) Hose pipe | 10,000,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
m) Others | NA | NA | NA | 19 | 12 |  |  |  |  |  |  | 

## Slide 12
mdbcf of Reliability verification trains (MDBF 100,000 km)
System/Subsystem / Equipment/Component | Target | MDBCF | Result | 6M failure | Nov/22 |  | System/Subsystem / Equipment/Component | Target | MDBCF | Result | 6M failure | Nov/22
Communication System | 15,000 | 17,778 | Pass | 29 | 13 |  | Couplers and Draft Gear | 200,000 | No Failure | Pass | 0 | 0
a) PIS control unit | 1,400,000 | 1,031,142 | Fail | 1 | 0 |  | a) Automatic coupler | 4,600,000 | No Failure | Pass | 0 | 0
b) Saloon control unit | 1,400,000 | No Failure | Pass | 0 | 0 |  | b) Semi permanent coupler | 7,000,000 | No Failure | Pass | 0 | 0
c) Main operational panel | 1,400,000 | No Failure | Pass | 0 | 0 |  | c) Others | NA | NA | NA | 0 | 0
d) Cab loudspeaker | 1,400,000 | No Failure | Pass | 0 | 0 |  | Bogies & Suspension | 150,000 | 46,870 | Fail | 11 | 8
e) Passenger emergency control unit | 1,400,000 | No Failure | Pass | 0 | 0 |  | a) Drive gear and coupling | 6,000,000 | No Failure | Pass | 0 | 0
f) Saloon loudspeaker(SLSP) | 1,400,000 | No Failure | Pass | 0 | 0 |  | b) Primary suspension | 8,000,000 | No Failure | Pass | 0 | 0
g) Dynamic route map(DRM) | 1,400,000 | 24,747,408 | Pass | 1 | 1 |  | c) Secondary suspension | 8,000,000 | No Failure | Pass | 0 | 0
h) 37 inches Liquid Crystal Display(LCD) | 1,400,000 | No Failure | Pass | 0 | 0 |  | d) ODD | 8,000,000 | 1,031,142 | Fail | 1 | 1
i) Cab switch(CSW) | 1,400,000 | No Failure | Pass | 0 | 0 |  | e) Vertical Damper | 8,000,000 | No Failure | Pass | 0 | 0
j) Saloon switch(SSW) | 1,400,000 | No Failure | Pass | 0 | 0 |  | f) Lateral Damper | 8,000,000 | No Failure | Pass | 0 | 0
k) Front display unit(FDU) | 1,400,000 | No Failure | Pass | 0 | 0 |  | g) Axle Bearing | 8,000,000 | No Failure | Pass | 0 | 0
l) Train number indicator(TNI) | 1,400,000 | No Failure | Pass | 0 | 0 |  | h) Others | NA | NA | NA | 10 | 7
m) Side display unit(SDU) | 1,400,000 | 6,186,852 | Pass | 1 | 0 |  | Lighting System | 1,000,000 | 32,223 | Fail | 16 | 11
n) Saloon camera(SCAM) | 1,400,000 | No Failure | Pass | 0 | 0 |  | a) Exterior Lights | 8,000,000 | 1,546,713 | Fail | 2 | 1
o) ODD camera(OCAM) | 1,400,000 | 1,031,142 | Fail | 1 | 1 |  | b) Interior Lights | 8,000,000 | 515,571 | Fail | 6 | 2
p) Track view camera(TCAM) | 1,400,000 | No Failure | Pass | 0 | 0 |  | f) Others | NA | NA | NA | 8 | 8
q) Front camera(FCAM) | 1,400,000 | 1,031,142 | Fail | 1 | 0 |  | TCMS | 1,090,000 | 193,339 | Fail | 16 | 7
r) Detrainment camera(DCAM) | 1,400,000 | No Failure | Pass | 0 | 0 |  | Structure and Vehicle Interior Fittings | 100,000 | 85,929 | Fail | 36 | 13
s) Pantograph monitoring camera(PCAM) | 1,400,000 | 1,031,142 | Fail | 1 | 0 |  | Fire Detection System | 5,000,000 | 90,983 | Fail | 34 | 13
t) Exterior camera(ECAM) | 1,400,000 | 2,062,284 | Pass | 2 | 0 |  | Wiper | 100,000 | 90,983 | Fail | 34 | 12
u) Network Video Recorder(NVR) | 1,400,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
v) External loudspeakers(ELSP) | 1,400,000 | No Failure | Pass | 0 | 0 |  |  |  |  |  |  | 
w) Others | NA | NA | NA | 21 | 11 |  |  |  |  |  |  | 

## Slide 13
7) Pattern Failure
Period: Oct-Nov 2022
Sub system | Equipment | Quantity per one trainset |  |  |  |  |  |  | Item MDBCF (equip-km/failure) | Item Failure Rate (Failure/km) | Predicted Failure No. | Result (Oct' 22 ~ Nov' 22) | Inconsistent with Predicted Failure | Result (Three or more) | Pattern Failure (Inconsistent & ≥3) | 2022 | 2022
 |  | DM | T | M | M | T | DM | Total |  |  | 0 |  |  |  |  | 1M | 2M
 |  | DM | T | M | M | T | DM | Total |  |  | 112,561 |  |  |  |  | 10 | 11
Door System |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | 
 | EDCU | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 5,468,750 | 1.83E-07 | 2 | 9 | Inconsistent | O | Pattern Failure | 7 | 2
 | LOS | 8 | 8 | 8 | 8 | 8 | 8 | 48 | 166,666,667 | 6.00E-09 | 0 | 3 | Inconsistent | O | Pattern Failure | 3 | 0
 | Saloon to cab door | 1 |  |  |  |  | 1 | 2 | 13,790,147 | 7.25E-08 | 0 | 17 | Inconsistent | O | Pattern Failure | 10 | 7
HVAC System |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | 
 | Smoke detector unit | 1 |  |  |  |  | 1 | 2 | 175,000,000 | 5.71E-09 | 0 | 10 | Inconsistent | O | Pattern Failure | 10 | 0
Communication System |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | 
Lighting System |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  | 
 | Interior Lights | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 30,158,494 | 3.32E-08 | 0 | 6 | Inconsistent | O | Pattern Failure | 4 | 2
TCMS |  | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 1,160,536 | 8.62E-07 | 1 | 12 | Inconsistent | O | Pattern Failure | 1 | 11
Structure and Vehicle Interior Fittings |  | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 191,335 | 5.23E-06 | 7 | 12 | Inconsistent | O | Pattern Failure | 1 | 11
Fire Detection System |  | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 5,608,974 | 1.78E-07 | 0 | 12 | Inconsistent | O | Pattern Failure | 1 | 11
Wiper |  | 3 |  |  |  |  | 3 | 6 | 215,255 | 4.65E-06 | 6 | 12 | Inconsistent | O | Pattern Failure | 1 | 11

## Slide 14
8) Availability of trains
SUMMARY of Availability Demonstration
No of Days in month | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30
Year | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022
Month | Apr | May | June | July | Aug | Sep | Oct | Nov
DT for 6M Avr. Availabiltiy Calculation |  |  |  |  |  |  |  | 
Line 2A & 7 | Stablization Period |  |  |  |  |  | 134,905 | 206,338
All |  |  |  |  |  |  | 134,905 | 206,338
Total Time for 6M Avr. Availability Calculation |  |  |  |  |  |  |  | 
Line 2A & 7 | Stablization Period |  |  |  |  |  | 758,880 | 734,400
All |  |  |  |  |  |  | 758,880 | 734,400
6M Avr. Availability |  |  |  |  |  |  |  | 
Line 2A & 7 | Stablization Period |  |  |  |  |  | 97.00% | 92.38%
All |  |  |  |  |  |  | 97.42% | 93.49%

## Slide 15: THANKS