## Slide 1: DMRC Contract RS8 Status update for Monthly Review /FRACAS Meeting-19.07.2017

## Slide 2: AGENDA
1 | Performance Review of Trains: Reliability Demonstration
1.1 | Kilometer mileage for June’17
1.2 | Mean Distance Between Failures (MDBF) Calculation
1.3 | Case-wise Reliability Failures Analysis
1.4 | System-wise Reliability Failures Analysis
1.5 | Monthly Performance of Last Six Months (System-wise)
2 | Previous month’s reliability failures pertaining to MELCO sub-systems
3 | MDBCF Failure
4 | Availability Report
5 | Monthly Review Point
6 | Summary of status of RS8 EIRs

## Slide 3
1. | Performance Review of Trains: Reliability Demonstration
1.1 | Kilometer mileage for June’17
SN | Train Set No. | KM as on 01.06.2017 | KM as on 30.06.2017 | KM Achieved in the month of June’17
1 | TS#01 | 93712 | 93712 | 0
2 | TS#02 | 95264 | 99955 | 4691
3 | TS#03 | 89863 | 94050 | 4187
4 | TS#04 | 103880 | 108199 | 4319
5 | TS#05 | 94024 | 98202 | 4178
6 | TS#06 | 103055 | 107284 | 4229
7 | TS#07 | 96763 | 100849 | 4086
8 | TS#08 | 95964 | 98874 | 2910
9 | TS#09 | 97001 | 101942 | 4941
10 | TS#10 | 94843 | 99477 | 4637
TOTAL |  |  | 1002544 | 38175

## Slide 4
1.2 | Mean Distance Between Failures (MDBF) Calculation |  |  |  |  | 
MDBF Calculation for complete reliability demonstration period (Oct’15-June’17): |  |  |  |  |  | 
Month |  | Running Mileage | No. of Reliability Failures | Train-set | Type of failure | MDBF
Oct’15 |  | 38458 | Nil |  |  | Pass
Nov’15 |  | 38345 | 2 | 1). TS10, 2). TS08 | 1). SIV ACC Unit 2). VCB Magnetic Valve | 19172.5
Dec’15 |  | 39473 | 2 | 1). TS10 2). TS02 | 1). Panto pneumatic fitting leakage 2). PT Fuse | 19736.5
Jan’16 |  | 39219 | Nil |  |  | Pass
Feb’16 |  | 36636 | Nil |  |  | Pass
Mar’16 |  | 39282 | 2 | TS01 & TS07 | Surge Capacitor | 19641
April’16 |  | 37801 | 1 | TS02 | BECU | 37801
May’16 |  | 39104 | 1 | TS02 | BECU | 39104
June’16 |  | 37885 | 1 | TS09 | DCU Connector | 37885
July’16 |  | 39210 | 2 | 1). TS02 2). TS01 | 1). Surge Capacitor 2). VCB | 19605
Aug’16 |  | 38900 | Nil |  |  | Pass
Sep’16 |  | 37760 | 1 | TS10 | HVAC | 37760
Oct’16 |  | 40757 | Nil |  |  | Pass
Nov’16 |  | 37875 | Nil |  |  | Pass
Dec’16 |  | 39396 | Nil |  |  | Pass
Jan’17 |  | 38609 | 1 | TS03 | Surge Capacitor | 38609
Feb’17 |  | 35214 | 3 | TS08, TS03 & TS09 | Surge Capacitor | 11738
Mar’17 |  | 38466 | 1 | TS01 | Surge Capacitor | 38466
April’17 |  | 38274 | Nil |  |  | Pass
May’17 |  | 39100 | 3 | 1). TS09 2). TS08 3). TS01 | 1). CMC Contactor 2). VCB 3). Battery | 13033.3
June’17 |  | 38175 | Nil |  |  | Pass

## Slide 5
1.3 | Case-wise Reliability Failures Analysis
SN | CASES | 2015 |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  | 
 |  | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Total
1 | Withdrawal | 0 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 3 | 0 | 16
2 | Delay | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
3 | De-boarding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pre- departure (Train detained in depot or siding after fitness) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Total |  | NIL | 2 | 2 | NIL | NIL | 2 | 1 | 1 | 1 | 2 | NIL | 1 | NIL | NIL | NIL | 1 | 3 | 1 | NIL | 3 | NIL | 20

## Slide 6
1.4 | System-wise Reliability Failures Analysis
SYSTEM | 2015 |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  | 
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Total
VEHICLE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
STRUCTURE & INTERIOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOGIE & SUSPENSION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GANGWAYS & COUPLERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRACTION | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6
BRAKE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
AUXILIARY ELECTICAL | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 1 | 0 | 9
DOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
PNEUMETIC & AIR DIS. SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMUNICATION SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ATC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 1 | 0 | 3 | 0 | 20

## Slide 7
1.5 | Monthly Performance of Last Six Months (System-wise)
SYSTEM | 2017 |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | June | Total nos. of failures in last six months | Total nos. of Failures in last three months
VEHICLE | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
STRUCTURE & INTERIOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BOGIE & SUSPENSION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GANGWAYS & COUPLERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRACTION | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
BRAKE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AUXILIARY ELECTICAL | 1 | 3 | 1 | 0 | 1* | 0 | 6* | 1
DOOR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HVAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PNEUMETIC & AIR DIS. SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMUNICATION SYSTEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ATC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 1 | 3 | 1 | 0 | 3 | 0 | 08 | 03

## Slide 8
2. | Previous month’s reliability failures pertaining to MELCO sub-systems. |  | 
SN | Description | Status/Action Plan | Target
i. | SIV ground fault, SIV major fault on TIMS (08 reliability failures). | During investigations, the ACC surge capacitor was found in burnt condition and replaced with a healthy spare. The defective items have been sent to MELCO Japan for further investigation. Fleet replacement of all SIV surge capacitors has been completed in all ten train-sets by 18th April’17. Further, as advised by MELCO design team, on 24th April’17, M/s. MEI depot team measured the current & voltage readings before & after SIVK with test software ver AJ04 (with SIVK 500ms delay) & AJ05 (with SIVK 1000ms delay). Further, on 1st July’17, the SIV software ver (AJ04), check sum(0343-636A) was uploaded in TS#08/DT1 and performed two round trips non-revenue trials at mainline and SIV operation was found normal during the trials. Therefore, it has been advised to keep TS#08/DT1-SIV under monitoring for one month (till 2nd Aug’17). Based on monitoring results, the SIV software ver (AJ04), check sum(0343-636A) will be proposed to be uploaded in all SIVs. | Aug’17
ii. | VCB Failures (03 reliability failures) | During investigations, the VCBs found malfunctioning. The fleet replacement of VCBs has been completed in all ten train-sets by 16th June’2017. The application of Raychem tape & insulation paint will be expedited by end of July’17. | Aug’17

## Slide 9
3. Between 5 Months To 12 Months Mean Distance Between Component Failure Report |  |  |  |  |  |  |  |  |  |  | 
No | System Equipment | Equipment | S.F Count | N.S.F Count | Chargeability BEML | Chargeability DMRC | MDBCF(KM) (Target) | Failure Rate (Target) | MDBCF (KM) Achived | Failure Rate (Achived) | Assesments
1 | Brake System | Air Suspension Equipment | 0 | 0 | 0 | 0 | 460000 | 2.17391E-06 | 0 | 0 | PASS
2 | Gangways and Couplers | Automatic Coupling Equipment | 0 | 0 | 0 | 0 | 4600000 | 2.17391E-07 | 0 | 0 | PASS
3 | Auxiliary Electrical System | Battery (KRM250X) | 0 | 0 | 0 | 0 | 10000000 | 0.0000001 | 0 | 0 | PASS
4 | Auxiliary Electrical System | Battery Charger Box | 0 | 0 | 0 | 0 | 896000 | 1.11607E-06 | 0 | 0 | PASS
5 | Communication Equipment | Communication Equipment | 0 | 0 | 0 | 0 | 830000 | 1.20482E-06 | 0 | 0 | PASS
6 | Traction System | Con/Inv Box | 0 | 0 | 0 | 0 | 410000 | 2.43902E-06 | 0 | 0 | PASS
7 | Auxiliary Electrical System | Converter Power Unit | 0 | 0 | 0 | 0 | 896000 | 1.11607E-06 | 0 | 0 | PASS
8 | Door System | Door System | 0 | 0 | 0 | 0 | 590000 | 1.69492E-06 | 0 | 0 | PASS
9 | Bogie and Suspensions | Drive System | 0 | 0 | 0 | 0 | 4400000 | 2.27273E-07 | 0 | 0 | PASS
10 | HVAC System | HVAC System | 0 | 0 | 0 | 0 | 410000 | 2.43902E-06 | 0 | 0 | PASS
11 | Structure and Vehicle Interior Fittings | LED Lighting System | 0 | 0 | 0 | 0 | 8000000 | 0.000000125 | 0 | 0 | PASS
12 | Traction System | Neutral Section Detector | 0 | 0 | 0 | 0 | 26000000 | 3.84615E-08 | 0 | 0 | PASS
13 | Bogie and Suspensions | Primary Suspension | 0 | 0 | 0 | 0 | 6500000 | 1.53846E-07 | 0 | 0 | PASS
14 | Bogie and Suspensions | Secondary Suspension | 0 | 0 | 0 | 0 | 6500000 | 1.53846E-07 | 0 | 0 | PASS
15 | Gangways and Couplers | Semi permanent coupler | 0 | 0 | 0 | 0 | 7000000 | 1.42857E-07 | 0 | 0 | PASS
16 | Train Management System | TIMS | 0 | 0 | 0 | 0 | 1192000 | 8.38926E-07 | 0 | 0 | PASS
17 | Traction System | Traction Motor | 0 | 0 | 0 | 0 | 2656000 | 3.76506E-07 | 0 | 0 | PASS
18 | Traction System | Main Transformer | 1 | 0 | 1 | 0 | 9173000 | 1.09016E-07 | 310286 | 3.22283E-06 | FAIL
19 | Traction System | Pantograph | 1 | 0 | 1 | 0 | 7900000 | 1.26582E-07 | 310286 | 3.22283E-06 | FAIL
20 | Traction System | VCB | 2 | 0 | 2 | 0 | 1404000 | 7.12251E-07 | 155143 | 6.44567E-06 | FAIL
21 | Others |  | 4 | 0 | 4 | 0 | 663814 | 1.6983334 | 390862 | 1.53429E-06 | FAIL

## Slide 10
After 12 Months Mean Distance Between Component Failure Report
No | System Equipment | Equipment | S.F Count | N.S.F Count | Chargeability BEML | Chargeability DMRC | MDBCF(KM) (Target) | Failure Rate (Target) | MDBCF (KM) Achived | Failure Rate (Achived) | Assesments
1 | Brake System | Air Suspension Equipment | 0 | 0 | 0 | 0 | 620000 | 1.6129E-06 | 0 | 0 | PASS
2 | Gangways and Couplers | Automatic Coupling Equipment | 0 | 0 | 0 | 0 | 8000000 | 0.000000125 | 0 | 0 | PASS
3 | Auxiliary Electrical System | Battery Charger Box | 0 | 0 | 0 | 0 | 1195000 | 8.3682E-07 | 0 | 0 | PASS
4 | Communication Equipment | Communication Equipment | 0 | 0 | 0 | 0 | 1000000 | 0.000001 | 0 | 0 | PASS
5 | Traction System | Con/Inv Box | 0 | 0 | 0 | 0 | 547000 | 1.82815E-06 | 0 | 0 | PASS
6 | Auxiliary Electrical System | Converter Power Unit | 0 | 0 | 0 | 0 | 1195000 | 8.3682E-07 | 0 | 0 | PASS
7 | Door System | Door System | 0 | 0 | 0 | 0 | 780000 | 1.28205E-06 | 0 | 0 | PASS
8 | Bogie and Suspensions | Drive System | 0 | 0 | 0 | 0 | 6000000 | 1.66667E-07 | 0 | 0 | PASS
9 | Structure and Vehicle Interior Fittings | LED Lighting System | 0 | 0 | 0 | 0 | 10000000 | 0.0000001 | 0 | 0 | PASS
10 | Traction System | Main Transformer | 0 | 0 | 0 | 0 | 12230000 | 8.17661E-08 | 0 | 0 | PASS
11 | Traction System | Neutral Section Detector | 0 | 0 | 0 | 0 | 5000000 | 0.0000002 | 0 | 0 | PASS
12 | Traction System | Pantograph | 0 | 0 | 0 | 0 | 10000000 | 0.0000001 | 0 | 0 | PASS
13 | Bogie and Suspensions | Primary Suspension | 0 | 0 | 0 | 0 | 10000000 | 0.0000001 | 0 | 0 | PASS
14 | Bogie and Suspensions | Secondary Suspension | 0 | 0 | 0 | 0 | 10000000 | 0.0000001 | 0 | 0 | PASS
15 | Gangways and Couplers | Semi permanent coupler | 0 | 0 | 0 | 0 | 16000000 | 6.25E-08 | 0 | 0 | PASS
16 | Train Management System | TIMS | 0 | 0 | 0 | 0 | 1589000 | 6.29327E-07 | 0 | 0 | PASS
17 | Traction System | Traction Motor | 0 | 0 | 0 | 0 | 3542000 | 2.82326E-07 | 0 | 0 | PASS
18 | Auxiliary Electrical System | Battery (KRM250X) | 1 | 0 | 1 | 0 | 10000000 | 0.0000001 | 405183 | 2.46802E-06 | FAIL
19 | HVAC System | HVAC System | 1 | 0 | 1 | 0 | 540000 | 1.85185E-06 | 405183 | 2.46802E-06 | FAIL
20 | Traction System | VCB | 2 | 0 | 2 | 0 | 1872000 | 5.34188E-07 | 202591.5 | 4.93604E-06 | FAIL
21 | Others |  | 8 | 0 | 8 | 0 | 683941 | 0.00000151 | 651767 | 1.53429E-06 | FAIL

## Slide 11
4. Availability Report From June’15 to June’17 |  |  |  |  | 
Trainset No. | CM Down Time | Total Time | Target (%) | Result With CM(%) | Result with CM Assessment
TS101 | 34 Day 09:55 | 789 Day 00:00 | 96.50 | 95.638 | FAIL
TS102 | 21 Day 23:04 | 789 Day 00:00 | 96.50 | 97.217 | PASS
TS103 | 26 Day 16:16 | 789 Day 00:00 | 96.50 | 96.619 | PASS
TS104 | 22 Day 06:10 | 789 Day 00:00 | 96.50 | 97.179 | PASS
TS105 | 14 Day 03:58 | 789 Day 00:00 | 96.50 | 98.205 | PASS
TS106 | 13 Day 10:55 | 789 Day 00:00 | 96.50 | 98.295 | PASS
TS107 | 18 Day 01:52 | 789 Day 00:00 | 96.50 | 97.709 | PASS
TS108 | 16 Day 08:46 | 789 Day 00:00 | 96.50 | 97.926 | PASS
TS109 | 23 Day 20:07 | 789 Day 00:00 | 96.50 | 96.979 | PASS
TS110 | 19 Day 08:40 | 789 Day 00:00 | 96.50 | 97.546 | PASS

## Slide 12
SN | Description |  | Status | Target
3. | Testing & commissioning |  |  | 
3.1 | Implementation of HVAC blower modification in line with RS3. |  | The existing 38 blade MS blowers of all Saloon HVACs of one train-set (TS02) have been replaced with 42 blade SS blowers on 11th July’17. The activity will be completed in remaining train-sets by Oct’17. | Sep’17
3.2 | Wi-Fi Commissioning. |  | PO has been placed on M/s. MEI. The commissioning work would start at depot by Dec’17. | Dec’17
4. | Action plan for closing remaining point of factory pending issues-Part A |  |  | 
4.1 | Replacement of Wheel set No. 00016 in TS01/DT2/Bogie No. T002. |  | The PO has been placed. The spare wheel set would be supplied by Sept’17. | Sept’17
5. | Spares |  |  | 
5.1 | DLP Spares | All required DLP spares have been positioned at depot. The majority of shortfall quantity of used items are being recouped regularly. The status/schedule of recoupment of items pertaining to MELCO is as under: i). SIV MCBRX Card: The delivery date will be informed by July’2017. ii). SIV ACC Unit (JMRC Loan): The delivery date will be informed by July’2017. |  | 
5.2 | Consumable Spares | The consumable spares required for performing A,B1,B2,B4 & B8 maintenance checks have been handed over to JMRC Custody Stores. The shortfall quantity of all used items is being recouped as per JMRC requirement. Regarding consumable spares required for C-1 check, majority of items have been handed over to JMRC. |  | 
5. Monthly Review Points

## Slide 13
SN | Description | Status | Target
6. | Training to JMRC Staffs: The training to JMRC staff on PA/PIS, Pantograph, Secondary suspension, CI/SIV/TIMS, CCTV, HVAC, Battery and Bogie systems have already been completed. The status of training on remaining systems are as below: |  | 
 | Gangway | The training topics along with budgetary offer and tentative schedule from OEM (M/s. Hubner) was submitted to DMRC vide BEML’s letter Ref: BEML/RS8/16-17/501 dt. 1st Aug’2016. DMRC’s approval (letter ref: DMRC/134/15/RS8/Training/6054 dt. 16th Sept’2016) on OEM’s budgetary offer has been received. Further, as advised vide DMRC’s letter (ref: DMRC/134/15/RS8/Training/6363 dt. 05th June’2017) this training has been postponed for next six months. | As per JMRC’s requirement
 | Coupler | The training topics along with budgetary offer from OEM (M/s. Voith) was submitted to DMRC vide BEML’s letter Ref: BEML/RS8/15-16/409 dt. 1st Sept’2015. DMRC’s approval (letter ref: DMRC/134/15/RS8/Training/6087 dt. 8th Nov’2016) on OEM’s budgetary offer (for providing heavy maintenance training) has been received and accordingly discussion with OEM was under progress. Further, DMRC vide letter (ref: DMRC/134/15/RS8/Training/6363 dt. 05th June’2017) has communicated that JMRC requires light maintenance training instead heavy maintenance training. Now, discussion with OEM is under progress accordingly. | Oct’17
 | Brake & Saloon Doors | The OEM’s proposal was submitted to DMRC vide BEML’s letter Ref: BEML/RS8/16-17/527 dt. 3rd Nov’2016. DMRC’s approval (letter ref: DMRC/134/15/RS8/Training/6200 dt. 30th Nov’2016) on OEM’s budgetary offer has been received. Now, discussion with OEM is under progress. | Oct’17

## Slide 14
SN | Description | Status | Target
7. | Pending RS3 SECP Implementation of TIMS system in one software version: i). PAEH Override ii). Message to pop-up on TIMS VDU if route not set by T.O. iii).Brake Redundancy. iv). Self Diagnostic function of DOS Card. | The technical proposal was submitted to DMRC vide letter ref: BEML/RS8/17-18/548 dt. 08.04.2017 and DMRC’s approval has been received vide letter ref: DMRC/134/15/RS8/HECP-SECP/6360 dt 05.06.2017. Now, the discussion is under progress with OEM for development of software. | Oct’17
8. | Proposal for installing fire & smoke detector/heat detector system in RS8 stock as advised vide DMRC letter No.DMRC/134/15/RS8/Misc./6357 dt. 15.05.17. | A presentation will be made by M/s. Consilium Marine India Pvt. Ltd and M/s. Fogtec India Pvt Ltd. during monthly review meeting on 19th July’17. | July’17
9. | Supply of Signage. | The label of “pregnant & lactate women reserved seat” and pink strips have already been supplied. Remaining labels have been received at BEML Bangalore and would be supplied to JMRC by July’17. | July’17

## Slide 15
SN | Description | Status | Target
10. | Status of implementation of RS3 HECPs in RS8 Trains |  | 
The status & target for the pending RS3 HECP implementation in RS8 train sets are as under: |  |  | 
i. | HECP-RS3-106 (PAEH circuit modification) | Hardware modification has been completed in all train sets and regarding TIMS S/W modification, discussion is under progress with M/s. MEI. | Oct’17
ii. | HECP-RS3-111 (Rev-2) (Motoring cut off in case of one bogie EB condition control circuit modification) | The hardware modification has been completed in four train sets (TS01,TS02,TS05 & TS06). Further, in view of recent failure in RS3, this modification has been revised & is under trial in RS3/RS9 project train-sets. The implementation of revised modification in RS8 will be done upon successful implementation in RS3/RS9. | Nov’17

## Slide 16
SN | Description | Status | Target
11. | Status of implementation of RS8 HECPs |  | 
i. | HECP-BEML-RS8-002 (Provision of flasher light and HVAC fresh air damper ON/OFF PB in Cab). | As per DMRC’s first stage approval, the modification has been implemented in two train-sets (TS02 & TS05). Now, JMRC is requested to release the joint note so that DMRC’s approval can be obtained to implement the modification in remaining train-sets. | Nov’17
ii. | HECP-BEML-RS8-004 (Installation of water guide plate to prevent water ingress in Cab through Cab Side Doors). | The DMRC’s approval (letter ref: DMRC/134/16/RS8/HECP-SECP/6349 dt 07.04.2017) has been received. The material has been arranged and JMRC is requested to allot train-sets for implementation of modification. | Oct’17
12. | Status of implementation of RS3 pending FMIs in RS8 Trains: |  | 
The status & target of the pending RS3 FMI implementation in RS8 train sets are as under: |  |  | 
i. | Implementation of Gangway FMI. | The material required for modification has been received at depot. The modification would be started by end of July’17. | Sep’17
ii. | Implementation of “Fresh Air damper opening to 110 mm” FMI. | This FMI has been implemented in one train-set (TS02) on 11th July’17 and will be implemented in remaining train-sets along with blower modification work. | Sep’17

## Slide 17
13. | Summary of status of RS8 EIRs | 
i. | Total EIRs generated by JMRC as on date | 23
ii. | Total EIR’s closed | 11 (EIR No. 3, 5,6,7,9,10,13,15,16,17,19)
iii. | EIR’s may be referred for closure in this month. | 01 (EIR No. 21)
iv. | EIR for which DMRC/JMRC (RS) has been requested to assist BEML/Alstom in getting approval of DMRC/JMRC S&T to upload new ATC software through M/s. Alstom for early closure of the issue. | 01 (EIR No. 8)
v. | Total EIR’s for which modification approval received from DMRC and procurement of material to implement the modification/countermeasure is under progress. | 02 (EIR No. 2 & 11)
vi. | Total EIR’s for which investigation/trial is under progress. | 06 (EIR No. 1, 12, 14, 18, 22 & 23)
vii. | EIR for which replacement material is under arrangement to address the issue. | 01 (EIR No. 20)
viii. | Total EIRs for which the countermeasure implementation work (inline with RS3/RS9) is under progress in RS8 train-sets. | 01 (EIR No. 4)

## Slide 18
SN |  | Description | Status | Target | 
Detailed Description & Status of Open EIRs |  |  |  |  | 
i. | EIR No. 01 (Sun blinds not functioning well) |  | There is no line failures of sun blind assembly in recent past. During daily fitness checks of the trains, it has been reported that the sun blind screen does not roll back completely in some instance if being operated multiple times however generally the operation was normal if it is operated once or twice. |  | 
ii. | EIR No. 02 (SIV Major Fault & INVOVD faults detected in TS#05 and during investigation it was observed that DT2 SIV Discharge unit got burnt). |  | M/s. MEI factory Bangalore has received the material for repairing the discharge unit from M/s. MELCO on 12th July’17. The repair of the Discharge unit is under progress at MEI factory. Regarding implementation of SIV front cover modification in RS8 project (in line with approved proposal of RS3), M/s. MEI depot team has received material (except adhesives). The modification work would start by end of July’17 when the pending material would be received. |  | Aug’17
iii | EIR No. 04 (Gap or Crown Height from journal box to bogie frame not in specified limit). |  | In-line with RS3/RS9, the activity of providing shims to maintain crown height has been completed in three train-sets (TS01, TS02 & TS05). JMRC is requested to provide remaining train-sets to expedite the work. |  | Oct’17
iv. | EIR No. 08 (PAEH unknown status on TIMS). |  | The issue of non compliance of DID requirement as per para no. 3.2.5 of ATC-PA&PIS INTERFACE SPECIFICATION JPJS02-SE-0022-A has been conveyed (vide BEML’s letter ref: BEML/RS8/ATL/17-18/551 dt 20.04.2017) to M/s. Alstom. M/s. Alstom (vide letter ref:ATL/DMRC/JP/JS02-Cont/0296 dt. 24th April’17) informed that the polling cycle has been tuned to its maximum limit in ATC onboard s/w [TDMS ver 4.5.10]. DMRC/JMRC RS is requested to assist BEML by taking up the issue with DMRC/JMRC S&T. |  | 

## Slide 19
SN | Description | Status | Target
v. | EIR No. 11 (During main line operation of RS8 trains in kite flying season, heavy flashing with blast sound were observed & OHE Tripped). | As advised by DMRC (vide letter ref: DMRC/134/15/RS8/HECP-SECP/5959 dt. 05.03.2016), BEML had submitted proposal for Pantograph painting (vide letter ref: BEML/RS8/16-17/515 dt. 16.09.2016) and the same has been approved by DMRC (vide letter ref: DMRC/134/15/RS8/HECP-SECP/6060 dt 27.09.2016). BEML has awarded PO to OEM (M/s. FTIL) to perform above said activity. The work implementation shall commence at depot by end of Aug’17. | Nov’17
vi. | EIR No. 12 (While passing neutral section, rear DT Car VCB open/trip message does not pop up on TIMS screen and also the message does not get logged in history page in Random trains). | M/s. MELCO had investigated the issue and implemented the SECP (RS8-TIMS-001) and accordingly the modified TIMS software (1.04) was uploaded in all train-sets to resolve the issue. But, the problem could not be resolved. Again, M/s. MELCO developed TIMS test software (Ver CPU4-1 1.06 & CPU-2 1.05) and uploaded in all RS8 trains to monitor and record the relevant data during “VCB open/trip” message not getting popup during revenue service as the reported phenomena are very infrequent. After uploading of TIMS new software, from 20th Feb’2017 to till date the problem was reported by JMRC twice. On 1st July’17, the TIMS software ver (1.07), check sum CPU4-1(1554) & CPU4-2(9D02) was uploaded in TS#08 and run the train on mainline towards monitoring Pop up of “VCB Open/Trip message” during NS negotiation & “ADCR de-energized when train is not stationary fault” and found the faults are popping up on TIMS VDU of both units as per logic. Further, this revised TIMS software has been uploaded in all train-sets (except TS01 which is under C-1 maintenance check). | Under Monitoring

## Slide 20
SN | Description | Status | Target
vii. | EIR No. 14 (SIV ground fault, SIV major fault in TS#07/D1B07 & TS#01/D1B01). | During investigation in TS#07, D1B07 ACC surge capacitor was found in burnt condition. During investigation in TS#01, D1B01 MTr Blower motor assembly and ACC surge capacitor were found in burnt condition. Above items were replaced with healthy spares and both trains were made fit for revenue service. The defective items have been sent to MELCO Japan for further investigation. Regarding frequent failure of surge capacitors in RS8 Train-sets, Fleet replacement of all SIV surge capacitors has been completed in all ten train-sets by 18th April’17. Further, as advised by MELCO design team, on 24th April’17, M/s. MEI depot team measured the current & voltage readings before & after SIVK with test software ver AJ04 (with SIVK 500ms delay) & AJ05 (with SIVK 1000ms delay). Further, on 1st July’17, the SIV software ver (AJ04), check sum(0343-636A) was uploaded in TS#08/DT1 and performed two round trips non-revenue trials at mainline and SIV operation was found normal during the trials. Therefore, it has been advised to keep TS#08/DT1-SIV under monitoring for one month (till 2nd Aug’17). Based on monitoring results, the SIV software ver (AJ04), check sum(0343-636A) will be proposed to be uploaded in all SIVs. | Aug’17

## Slide 21
SN | Description | Status | Target
viii. | EIR No. 18 (Occurrence of saloon door obstruction/detection failure & door showing faulty on TIMS fault being reported in ID-105 Trains during summer season). | As advised by JMRC in weekly review meeting on 31.05.2016, the following DCUs were relocated in TS#07 at similar location for monitoring their performance in high temp. by positioning the train under sun light. i). D1A08 DRR1 ii). D1A02 DRL1 iii). D1B03 DRR2 iv). D1B03 DRR3 v). M1B01 DRL4 Further, on 18th June’16, TS07 was kept under sun light for monitoring the performance. The OEM’s field observation report has been submitted through email on 11th July’16. Further, based on KBI’s field observation, 05 nos. suspected DCUs were replaced with new ones in TS#07 on 10th Aug’16 by KBI and the old ones were sent to OEM (M/s. IFE-V) for testing (Burn In, high voltage & functional) and during testing DCUs have not shown any problem. The OEM’s investigation report has been submitted to DMRC/JMRC vide email dt. 01st March’17. Further to above, M/s. KBI has identified 18 saloon doors in five train-sets (TS02, TS03, TS05, TS07 & TS10) and pasted the temperature strips on DCUs to monitor the temperature up to July’17. | 

## Slide 22
SN | Description | Status | Target
ix. | EIR No. 20 (Swelling observed in LHS Cab side door of TS04/D1B04). | One set of Cab Side Doors have been supplied by OEM and received at BEML Bangalore. The material would be dispatched to depot by July’17. | July’17
x. | EIR No. 21 (Air leakage from Single Hose Protection Valve). | The OEM’s investigation report has been submitted vide e-mail dt. 19th June’17. Therefore, the EIR No. 21 may be referred for closure. | 
xi. | EIR No. 22 (TS01/M1A01 Battery Bank Failure). | The issue is under investigation by OEM (M/s. HBL) and the investigation results will be submitted by Aug’17. | Aug’17
xii. | EIR No. 23 (Burnt Marks noticed on TIMS Interface Card of TS01/D1A01 & TS03/D1B03). | The issue is under investigation. | ASAP

## Slide 23: THANK YOU